2024 Procurement in Excess of € 10m

| Project Details |  |
| --- | --- |
| Year: | 2024 |
| Parent Department: | Kerry County Council |
| Name of Contracting Body: | Kerry County Council |
| Name of Project/Description: | N69 Listowel Bypass Scheme |
| Procurement Details |  |
| Advertisement Date: | 28/05/2021 |
| Tender Advertised in: | OJEU Website/ Etenders Website |
| Awarded to: | Wills Bros Ltd., Ballylahan Bridge, Foxford, Co. Mayo |
| EU Contract Award Notice Date: | April 2022 |
| Contract Price: | €31,620,483.31 ex. VAT |
| Progress |  |
| Start Date: | February 2022 |
| Expected Date of Completion per Contract: | June 2024 |
| Spend in Year under Review (2024) | €6,141,830.67 ex. VAT |
| Cumulative Spend to End of Year (2024) | €46,689,000.00 ex. VAT |
| Projected Final Cost: | €47,400,000.00 ex. VAT |
| Value of Contract Variations: | 3 No Conciliators Recommendation received. 3 No Formal Change Order submitted to TII & CEO approved. CO1 – €5,631,902.79 ex VAT CO2 -€5,270,015.90 ex VAT FASA – €4,877,598.00 ex VAT |
| Date of Completion (estimated)--end of maintenance period | June 14th 2026 |
| Outputs |  |
| Expected Output on Completion (E.G. XX kms of Road, No of units etc) | 3.65km of offline road construction as well as the online upgrade of 2.30km of an existing section of urban road. |
| Output Achieved to date (E.G. X kms of Roads, No of Units etc) | 3.65km of offline road construction as well as the online upgrade of 2.30km of an existing section of urban road. |